ICT Infrastructure Development and Expansion Desk Leader

Competency Test: Test Blueprint and Item Bank

Draft 3. Full blueprint and all 120 items (Work 31, People 38, Results 51) for review.

# 1. Test parameters

| Job position | ICT Infrastructure Development and Expansion Desk Leader |
| --- | --- |
| Job category type | Leader |
| Job category level | To be confirmed (Leader I / II / III) |
| Competency framework | 12 technical competency units in 3 domains: Work, People, Results |
| Item format | Multiple choice, four options, one correct answer |
| Total items | 120 (Work 31, People 38, Results 51) |
| Cognitive weights | Remembering 8%, Understanding 22%, Application 37%, Analysis 23%, Evaluation 6%, Creation 4% |
| Difficulty ratio | Easy 20% : Moderate 50% : Difficult 30% (2:5:3) |
| Sources | Job description (major duties table T1-T44; main duties list M1-M80); Test Blueprint training slides |

# 2. Blueprint summary

| Domain | Units | Sub-comp. | Items | Weight | Re | Un | Ap | An | Ev | Cr |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work | 4 | 5 | 31 | 26% | 3 | 7 | 11 | 7 | 2 | 1 |
| People | 4 | 6 | 38 | 32% | 3 | 9 | 14 | 9 | 2 | 1 |
| Results | 4 | 8 | 51 | 42% | 4 | 11 | 19 | 12 | 3 | 2 |
| Total | 12 | 19 | 120 | 100% | 10 | 27 | 44 | 28 | 7 | 4 |
| Cognitive weight |  |  |  |  | 8% | 22% | 37% | 23% | 6% | 4% |

Re = Remembering, Un = Understanding, Ap = Application, An = Analysis, Ev = Evaluation, Cr = Creation. Domain and cognitive totals follow the worked Leader example in the training slides.

## Difficulty distribution

| Domain | Easy | Moderate | Difficult | Total |
| --- | --- | --- | --- | --- |
| Work | 7 | 14 | 10 | 31 |
| People | 8 | 19 | 11 | 38 |
| Results | 9 | 27 | 15 | 51 |
| Total | 24 | 60 | 36 | 120 |
| Target ratio | 20% | 50% | 30% | 100% |

Figures reflect the items as written in Sections 5 to 7 (see the coverage check in Section 8). Difficulty follows the slide logic: Remembering is easy; Understanding is split easy and moderate; Application and Analysis are split moderate and difficult; Evaluation and Creation are difficult.

# 3. Detailed blueprint by sub-competency

| ID | Unit and sub-competency | Items | Wt % | Re | Un | Ap | An | Ev | Cr |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| WORK DOMAIN |  |  |  |  |  |  |  |  |  |
| 1.1 | Unit 1: Strategy and Strategic Planning Aligning plans and roadmaps with national strategy | 8 | 6.7 | 1 | 2 | 3 | 2 |  |  |
| 1.2 | Unit 1: Strategy and Strategic Planning Formulating and revising policies, strategies and standards | 6 | 5.0 |  | 1 | 2 | 2 | 1 |  |
| 2.1 | Unit 2: Planning Annual and operational planning | 7 | 5.8 | 1 | 2 | 3 | 1 |  |  |
| 3.1 | Unit 3: Organizing Resources and Inputs Resource estimation, technical specifications and procurement inputs | 5 | 4.2 |  | 1 | 2 | 1 | 1 |  |
| 4.1 | Unit 4: Using Technology Using digital tools and information systems for Desk management | 5 | 4.2 | 1 | 1 | 1 | 1 |  | 1 |
| PEOPLE DOMAIN |  |  |  |  |  |  |  |  |  |
| 5.1 | Unit 5: Knowledge Data-center, cloud and shared infrastructure | 7 | 5.8 | 1 | 2 | 2 | 2 |  |  |
| 5.2 | Unit 5: Knowledge Network, connectivity, security and resilience | 7 | 5.8 | 1 | 1 | 3 | 2 |  |  |
| 6.1 | Unit 6: Skill Research, needs assessment and evidence-based analysis | 7 | 5.8 |  | 2 | 2 | 2 | 1 |  |
| 6.2 | Unit 6: Skill Technical review, standards and interoperability | 6 | 5.0 |  | 1 | 3 | 1 | 1 |  |
| 7.1 | Unit 7: Professional Ethics Professional ethics and accountability in public ICT work | 5 | 4.2 |  | 1 | 3 | 1 |  |  |
| 8.1 | Unit 8: Leading Leading and developing the Desk team | 6 | 5.0 | 1 | 2 | 1 | 1 |  | 1 |
| RESULTS DOMAIN |  |  |  |  |  |  |  |  |  |
| 9.1 | Unit 9: Decision-Making Evidence-based decisions and options analysis | 7 | 5.8 |  | 1 | 2 | 2 | 1 | 1 |
| 9.2 | Unit 9: Decision-Making Risk-informed decisions and corrective action | 6 | 5.0 |  | 1 | 3 | 2 |  |  |
| 10.1 | Unit 10: Monitoring and Effective Performance Monitoring plan and project implementation | 7 | 5.8 | 1 | 2 | 3 | 1 |  |  |
| 10.2 | Unit 10: Monitoring and Effective Performance Monitoring availability, capacity, utilization and accessibility | 7 | 5.8 | 1 | 2 | 2 | 2 |  |  |
| 11.1 | Unit 11: Evaluating Evaluating utilization and results | 7 | 5.8 | 1 | 1 | 3 | 1 | 1 |  |
| 11.2 | Unit 11: Evaluating Compliance and standards assessment | 7 | 5.8 |  | 2 | 2 | 2 | 1 |  |
| 12.1 | Unit 12: Feedback Service-user and stakeholder communication and feedback | 5 | 4.2 | 1 | 1 | 2 | 1 |  |  |
| 12.2 | Unit 12: Feedback Lessons learned and knowledge feedback loop | 5 | 4.2 |  | 1 | 2 | 1 |  | 1 |

# 4. Contents and outcomes to be measured

| ID | Sub-competency | Contents | Outcomes to be measured |
| --- | --- | --- | --- |
| 1.1 | Aligning plans and roadmaps with national strategy | Planning hierarchy (national digital strategy > Ministry strategic plan > annual institutional plan > Desk plan); infrastructure roadmaps; priority setting and sequencing; budget constraints | Identify the sources of the Desk plan; translate national priorities into Desk activities; prioritize and sequence initiatives; detect misalignment |
| 1.2 | Formulating and revising policies, strategies and standards | Desk role in policy formulation; evidence for policy inputs; stakeholder consultation and validation; implementability of policies; measurable standard provisions | Explain the Desk's policy role; select evidence for policy input; resolve stakeholder objections; diagnose implementation problems; judge the quality of draft provisions |
| 2.1 | Annual and operational planning | Plan elements; outputs vs outcomes; indicators and targets; timelines and dependencies; cascading plans to staff; mid-year plan adjustment | State plan elements; distinguish outputs from outcomes; write measurable indicators; sequence activities; adjust plans to new mandates; spot plan weaknesses |
| 3.1 | Resource estimation, technical specifications and procurement inputs | Capacity and resource estimation; shared vs dedicated resources; technical specifications and terms of reference; technical bid evaluation | Explain the role of specifications; prepare brand-neutral specifications; estimate procurement timing; compare resource options; recommend on technical evaluation |
| 4.1 | Using digital tools and information systems for Desk management | Work-management tools; reporting templates; infrastructure inventory and information systems; data quality and completeness | Identify suitable tools; explain benefits of digital tracking; apply tools to reporting; interpret incomplete data; design an information system |
| 5.1 | Data-center, cloud and shared infrastructure | Primary, backup and DR sites; hosting, storage, virtualization; cloud service and deployment models; high availability; capacity planning; data sovereignty; recovery objectives | Recall key concepts; explain how components and models differ; apply them to government hosting scenarios; analyze capacity and architecture options |
| 5.2 | Network, connectivity, security and resilience | Connectivity gaps and capacity; redundancy and single points of failure; access control; hardening; monitoring; incident response; business continuity; coordination with cybersecurity bodies | Recall resilience and security concepts; apply them to design and gap situations; analyze failure and risk scenarios |
| 6.1 | Research, needs assessment and evidence-based analysis | Research process from problem identification to presentation of findings; needs and gap assessment; benchmarking and adapting good practice; emerging-technology assessment; concept notes | Explain research steps and purposes; apply them to assessment tasks; analyze findings; judge the quality of evidence and recommendations |
| 6.2 | Technical review, standards and interoperability | Review of designs, architectures and technical proposals; compliance with approved standards; interoperability and compatibility; quality assurance; completion and acceptance reports | Explain interoperability and review purposes; apply review criteria to proposals; identify non-conformities; judge design or proposal quality |
| 7.1 | Professional ethics and accountability in public ICT work | Integrity in procurement; conflict of interest; vendor neutrality; confidentiality and data protection; transparency; accountability for public resources; equity of access | Explain ethical principles; apply them to workplace dilemmas; analyze conduct in cases |
| 8.1 | Leading and developing the Desk team | Work assignment and cascading; coaching and feedback; performance appraisal; competency-gap analysis; capacity building; teamwork; knowledge institutionalization | Recall leadership duties; explain performance-management principles; apply them to staff situations; design a capacity-development approach |
| 9.1 | Evidence-based decisions and options analysis | Option criteria (cost, performance, scalability, availability, security, data sovereignty, interoperability, sustainability, operations); recommendations; concept notes | Explain decision criteria; compare options; justify recommendations; judge and design decision packages |
| 9.2 | Risk-informed decisions and corrective action | Infrastructure risk identification and mitigation; single points of failure; prioritization under constraints; corrective decisions and escalation | Explain risk concepts; apply mitigation to scenarios; analyze trade-offs and choose corrective actions |
| 10.1 | Monitoring plan and project implementation | Tracking scope, schedule, budget and quality; milestones; deviations and bottlenecks; corrective actions; periodic reporting | Recall monitoring elements; explain their purpose; apply them to project data; analyze deviations |
| 10.2 | Monitoring availability, capacity, utilization and accessibility | Availability, capacity and utilization indicators; underutilized assets; regional accessibility; shared-infrastructure performance | Recall indicators; explain their meaning; apply them to data; analyze causes of underutilization |
| 11.1 | Evaluating utilization and results | Post-implementation reviews; outputs vs outcomes; M&E framework and indicators; benefit realization; utilization evaluation | Recall evaluation elements; explain output vs outcome; apply to cases; judge whether results are achieved |
| 11.2 | Compliance and standards assessment | Compliance monitoring mechanisms; assessment design; non-compliance analysis; corrective recommendations; technical guidance to institutions | Explain compliance mechanisms; apply assessment to cases; analyze non-compliance; judge corrective proposals |
| 12.1 | Service-user and stakeholder communication and feedback | Communication channels; collecting requirements and complaints; follow-up on responses; information exchange; stakeholder forums; dissemination of approved standards | Recall channels; explain feedback purpose; apply to user and stakeholder situations; analyze feedback data |
| 12.2 | Lessons learned and knowledge feedback loop | Lessons learned; good practices; knowledge sharing; feeding findings into plans and policies; institutional memory; technical manuals | Explain lesson capture; apply to cases; analyze recurring problems; design a knowledge feedback mechanism |

The generic framework units (for example Knowledge and Skill) are filled with the technical content of this JD: ICT infrastructure knowledge sits under Knowledge, research and technical review under Skill, and stakeholder communication under Feedback.

# 5. Work domain items (31)

Reference codes: T = number in the JD major duties table; M = number in the JD main duties list. Each item shows its key and rationale for reviewers; remove these lines for the exam version.

W-01  Sub-competency 1.1 | Remembering | Easy | JD: T1

On which combination of sources must the Desk's annual operational plan primarily be based?

A.	The previous year's Desk plan, staff work preferences, offers received from technology vendors and the Desk's available equipment

B.	The Ministry's strategic plan, the annual institutional plan, national digital priorities, the approved budget and the mandates assigned to the Desk

C.	Requests received from regional offices, development-partner project lists and activities left unfinished from the previous year

D.	The Desk's completed projects, professional staff job descriptions, current market prices and the Ministry's procurement records

Key: B.  The JD requires the annual plan to be derived from the Ministry's strategic and annual plans, national digital priorities, the approved budget and assigned mandates. Other sources may inform the plan but cannot replace these.

W-02  Sub-competency 1.1 | Understanding | Easy | JD: T1, M2

Why should the Desk's infrastructure roadmap be aligned with the national digital transformation strategy?

A.	So that the Desk no longer needs to prepare its own annual and operational plans

B.	So that all infrastructure can be purchased from one approved supplier to reduce costs

C.	So that the number of institutions the Desk must coordinate with is reduced

D.	So that infrastructure investments directly support national digital priorities rather than being pursued as isolated institutional projects

Key: D.  Alignment ensures infrastructure investment serves national priorities and avoids fragmented, isolated projects. It does not replace the Desk's own planning or dictate a single supplier.

W-03  Sub-competency 1.1 | Understanding | Moderate | JD: T19, M4

Which statement best distinguishes an infrastructure development roadmap from the Desk's annual operational plan?

A.	The roadmap sets out prioritized and sequenced infrastructure development over several years; the annual plan breaks the current year's share into activities, targets, timelines and responsibilities

B.	The roadmap lists the equipment to be purchased; the annual plan lists the staff who will operate it

C.	The roadmap is prepared by the Desk together with technology vendors; the annual plan is prepared by the Ministry's finance unit

D.	The roadmap covers only new infrastructure; the annual plan covers only maintenance of existing infrastructure

Key: A.  A roadmap is the multi-year, prioritized and sequenced framework; the annual plan is its operational, time-bound breakdown with targets and responsibilities.

W-04  Sub-competency 1.1 | Application | Moderate | JD: T1, M2

The Ministry's strategic plan sets the goal of extending shared hosting and connectivity to regional government offices. You are preparing the Desk's annual plan. Which planned activity best translates this goal into the plan?

A.	Promote awareness of digital transformation among regional government leaders through general visits

B.	Procure additional servers for the headquarters data center to improve national hosting capacity

C.	Assess hosting and connectivity gaps in the targeted regional offices, then prepare an expansion proposal with targets, timelines and required resources

D.	Hold regional consultation meetings whenever invitations are received from regional administrations

Key: C.  A strategic goal must be converted into a concrete, measurable Desk activity, here a gap assessment leading to a costed expansion proposal. The other options are vague, misdirected or merely reactive.

W-05  Sub-competency 1.1 | Application | Moderate | JD: T1, T19

A national digital priority requires 40 federal institutions to be onboarded to a shared government hosting platform over three years. How should this be reflected in the Desk's annual plan for Year 1?

A.	Plan to onboard all 40 institutions in Year 1 so that the target is certain to be met

B.	Set a Year 1 onboarding target consistent with the three-year roadmap, with milestones, responsible staff and required resources

C.	Leave the activity out of the Year 1 plan and include it only in the Year 3 plan

D.	List 'shared hosting onboarding' as a general activity without targets so the plan remains flexible

Key: B.  An annual plan carries the year's share of a multi-year target, with milestones, owners and resources. Over-committing, omitting the activity or leaving it unmeasured all undermine monitoring.

W-06  Sub-competency 1.1 | Application | Difficult | JD: T1, M1

After the Desk's roadmap was drafted, the approved budget turned out to be 30% lower than expected, while national digital priorities have not changed. What should the Desk Leader do when finalizing the annual plan?

A.	Rank roadmap activities by contribution to national priorities and readiness, defer the lowest-ranked ones to fit the budget, and document the revised targets and justification for approval

B.	Keep every activity in the plan and request additional funds once implementation has started

C.	Reduce the target of every activity by 30% so that all activities remain in the plan

D.	Suspend the roadmap until the full budget is restored and plan only routine administrative tasks

Key: A.  Under budget constraints the leader must prioritize transparently against national priorities and readiness, and obtain approval for revised targets. Across-the-board cuts or open-ended suspension ignore priorities.

W-07  Sub-competency 1.1 | Analysis | Moderate | JD: T28, M20

A draft Desk roadmap contains five projects. Each project buys separate servers and storage for one institution, and none uses common platforms, although a national priority calls for interoperable, shared digital environments. Which analysis is most accurate?

A.	The roadmap is aligned, because servers and storage are core infrastructure needed by every institution

B.	The roadmap is aligned, provided each institution's project stays within the approved budget

C.	The roadmap's main weakness is the number of projects, not how they relate to national priorities

D.	The roadmap is not aligned with the national priority because it favors fragmented, institution-specific investments over shared and interoperable infrastructure

Key: D.  The projects create isolated, non-shared environments, which contradicts the priority for shared and interoperable infrastructure. Being core infrastructure or within budget does not make them aligned.

W-08  Sub-competency 1.1 | Analysis | Difficult | JD: T19, M4, M11

The Desk can start only one initiative in the first quarter. The options are: (1) a shared government cloud platform on which twelve institutions have planned their digital services; (2) an upgrade of the office network of one institution whose current network is functioning; (3) a pilot of an emerging technology for which no institution has requested support. Which choice is best justified?

A.	Initiative 2, because it is the smallest and easiest to complete within the first quarter

B.	Initiative 3, because early adoption of emerging technology places the country ahead of others

C.	Initiative 1, because many planned national digital services depend on it and delay would hold up other institutions' progress

D.	Any of the three, because all infrastructure projects contribute equally to national priorities

Key: C.  Sequencing should favor enabling infrastructure on which many other initiatives depend. Ease of completion or novelty is not a valid priority criterion.

W-09  Sub-competency 1.2 | Understanding | Easy | JD: T30, T31

Which statement best describes the Desk's role in formulating national ICT infrastructure policies and standards?

A.	It contributes technical evidence, research findings, infrastructure assessments and stakeholder requirements, and participates in consultations and validation

B.	It approves final policies on behalf of the Ministry once technical committees have reviewed them

C.	It waits for policies to be prepared by other bodies and is responsible only for implementing them

D.	It prepares policies independently and submits them without consulting other institutions, to save time

Key: A.  The Desk supplies technical evidence and stakeholder requirements and takes part in consultation and validation. Approval rests with the competent authorities.

W-10  Sub-competency 1.2 | Application | Moderate | JD: T31, M16

The Desk is asked to contribute to the revision of the national data-center guideline. Which combination of evidence would best support a well-founded contribution?

A.	Vendor brochures describing the latest data-center equipment and its pricing

B.	Findings from data-center assessments and compliance reviews, service-user requirements, and benchmarking against other countries' practices

C.	The text of the current guideline and the opinions of the Desk's senior staff

D.	Complaints from a few institutions about the difficulty of the current guideline

Key: B.  A sound policy contribution rests on several relevant, independent sources of evidence. Vendor material, opinion or isolated complaints are insufficient or biased.

W-11  Sub-competency 1.2 | Application | Difficult | JD: T31, T32, M17

During consultation on a draft standard, regional institutions object that requiring dual power and cooling redundancy for every server room is unaffordable for small offices. The Desk's assessments show this redundancy is essential for facilities hosting critical national services. What is the best recommendation?

A.	Keep the requirement uniform for all facilities so that the standard remains simple to communicate and check

B.	Remove the redundancy requirement from the standard, since it cannot be met by all institutions

C.	Exempt regional institutions from the requirement without further analysis, to preserve good relations

D.	Propose requirements differentiated by facility category and criticality, supported by cost and risk evidence, and record the reasoning in the consultation report

Key: D.  Differentiating by criticality keeps protection where it matters while keeping the standard affordable and implementable. Uniform application, removal or unexplained exemption each undermine feasibility or quality.

W-12  Sub-competency 1.2 | Analysis | Moderate | JD: T35, T31

Compliance assessments show that eight of ten institutions fail one requirement of a national infrastructure standard. Before concluding that the institutions are at fault, what should the Desk analyze first?

A.	Which institutions failed most seriously, so that they can be reported for sanction

B.	Whether other standards can be withdrawn to reduce the overall compliance burden

C.	Whether the requirement is clear, technically feasible, well communicated and resourced, or whether the standard itself needs revision

D.	Whether vendors can supply equipment that automatically meets the requirement

Key: C.  A high failure rate on a single requirement often signals a problem with the requirement itself (clarity, feasibility, communication, resources). The cause should be diagnosed before blame is assigned.

W-13  Sub-competency 1.2 | Analysis | Difficult | JD: T31, T18

A draft national strategy states: 'All government institutions shall migrate all their systems to the government cloud within one year.' Known conditions are limited regional bandwidth, many legacy applications, no agreed cost model and no data classification. Which analysis is most accurate?

A.	The target is not implementable as written because its prerequisites are unaddressed; a phased migration with readiness criteria should be recommended

B.	The target is sound because ambitious deadlines accelerate implementation and force institutions to solve problems

C.	The target is acceptable, and only the length of the deadline needs to change to two years

D.	The target should be dropped, since government systems should never be hosted on cloud infrastructure

Key: A.  A target without its enabling conditions is not implementable. A phased, criteria-based approach addresses connectivity, classification, cost and legacy issues; extending the deadline or rejecting cloud outright does not.

W-14  Sub-competency 1.2 | Evaluation | Difficult | JD: T30, T34

Which draft provision is best formulated so that compliance with a national data-center standard can later be verified objectively?

A.	'Primary data centers shall have adequate backup power for their needs.'

B.	'Primary data centers should consider the use of backup power wherever this is possible.'

C.	'Primary data centers shall follow international best practice on power supply.'

D.	'Primary data centers shall have backup power able to sustain critical loads for a defined minimum duration, verified through documented annual tests.'

Key: D.  A verifiable provision states a specific, measurable requirement and a means of verification. 'Adequate', 'should consider' and 'best practice' are too vague to assess objectively.

W-15  Sub-competency 2.1 | Remembering | Easy | JD: T1

Which set of elements must the Desk's annual plan contain?

A.	Objectives, activities, staff names and a list of equipment to be purchased

B.	Objectives, activities, outputs, indicators, targets, timelines, responsibilities and resource requirements

C.	Objectives, budget lines, a procurement schedule and vendor contacts

D.	Activities, targets, the staff leave schedule and a summary of the previous year's report

Key: B.  The JD specifies that the annual plan contains objectives, activities, outputs, indicators, targets, timelines, responsibilities and resource requirements.

W-16  Sub-competency 2.1 | Understanding | Easy | JD: T4

What is the main purpose of cascading the Desk's plan and performance targets to individual staff?

A.	To transfer responsibility for meeting the Desk's targets from the leader to the professionals

B.	To reduce the need for the Desk Leader to monitor and evaluate staff performance

C.	To ensure that every employee has clear work targets aligned with the Desk's and the institution's plans

D.	To provide a basis for allocating the Desk's budget among individual employees

Key: C.  Cascading gives each employee clearly defined targets aligned with the Desk and institutional plans. It does not remove the leader's monitoring role or accountability.

W-17  Sub-competency 2.1 | Understanding | Moderate | JD: T21, T40

Which pair correctly distinguishes an output from an outcome in the Desk's work on infrastructure utilization?

A.	Output: twelve utilization assessments completed; outcome: improved use of installed infrastructure for government services

B.	Output: improved use of installed infrastructure for government services; outcome: twelve utilization assessments completed

C.	Output: satisfaction of institutions with the Desk; outcome: number of workshops organized

D.	Output and outcome are the same when both are measured at the end of the fiscal year

Key: A.  Outputs are the products of activities (assessments completed); outcomes are the results they lead to (improved utilization). The JD stresses that installing infrastructure is an output and effective utilization is the result.

W-18  Sub-competency 2.1 | Application | Moderate | JD: T1, T18

The Desk plans to complete infrastructure gap assessments for 30 regional institutions during the fiscal year. Which is the best-formulated indicator and target?

A.	Conduct gap assessments in regional institutions as far as possible during the year

B.	Improve the quality of gap assessments in regional institutions during the year

C.	Number of staff assigned to gap assessments during the year

D.	Number of targeted institutions with completed gap-assessment reports: 30 (100%) by the end of Quarter 4, including 15 by the end of Quarter 2

Key: D.  A good indicator is specific and measurable with a numeric target, a time frame and interim milestones. The other options describe activities or inputs without measurable results.

W-19  Sub-competency 2.1 | Application | Moderate | JD: T19, M45

Which sequence of planned activities is logically sound for developing a new infrastructure expansion project?

A.	Technical specification, needs assessment, project concept, stakeholder validation of gaps, roadmap

B.	Needs assessment, stakeholder validation of gaps, roadmap, project concept, technical specification

C.	Roadmap, technical specification, needs assessment, project concept, stakeholder validation of gaps

D.	Project concept, roadmap, technical specification, stakeholder validation of gaps, needs assessment

Key: B.  Needs must be assessed and validated before the roadmap is prepared, and the roadmap precedes the project concept and technical specification. The other sequences place design before evidence.

W-20  Sub-competency 2.1 | Application | Difficult | JD: T2, T44

In the middle of the year the Ministry gives the Desk an urgent new mandate, to assess the disaster-recovery readiness of critical government systems, without extra staff or budget. What is the best action regarding the approved plan?

A.	Add the new mandate to the plan and ask staff to complete all activities, including the new one, without any changes

B.	Postpone the new mandate to next year's plan, since the current plan has already been approved

C.	Assess the effect on existing activities, propose adjustments by deferring lower-priority ones, obtain approval for the revised plan and communicate the changes to staff

D.	Cancel the current plan and prepare a completely new plan based on the new mandate alone

Key: C.  A mid-year mandate calls for controlled re-planning: assess the impact, reprioritize, obtain approval and communicate. Absorbing the work silently or ignoring it breaks accountability.

W-21  Sub-competency 2.1 | Analysis | Moderate | JD: T1, T2

A draft Desk plan lists activities such as 'hold coordination meetings' and 'conduct assessments', with indicators like 'number of meetings held'. It has no responsible persons or timelines. What is the most serious weakness for later monitoring?

A.	The plan has too many activities for the Desk to be able to monitor

B.	The plan does not name the vendors who will supply the equipment

C.	The plan does not include a summary of previous years' results

D.	Without responsible persons, timelines and result-oriented indicators, progress cannot be tracked and accountability for results is unclear

Key: D.  Monitoring needs owners, timelines and result-oriented indicators. Counts of activities alone do not show progress toward outcomes.

W-22  Sub-competency 3.1 | Understanding | Moderate | JD: M46

What is the main purpose of the technical specifications that the Desk contributes to an infrastructure procurement document?

A.	To define the required technical characteristics and standards so that offers can be compared fairly and the infrastructure fits the approved architecture

B.	To indicate the brand and model that the Ministry prefers to buy

C.	To set the maximum price that the Ministry is willing to pay

D.	To limit the number of bidders to those already known to the Desk

Key: A.  Technical specifications set the objective, brand-neutral requirements against which offers are compared and ensure fit with approved architecture and standards.

W-23  Sub-competency 3.1 | Application | Moderate | JD: M46, M21

The Desk is preparing technical input for the procurement of storage for a shared government hosting platform. Which approach to the specification is most appropriate?

A.	Name the brand and model already used in the Ministry, because it is known to work

B.	Copy the specification from a vendor's brochure so that the equipment is certain to be available

C.	State the required capacity, performance, availability, interoperability and standards compliance without naming a brand

D.	Keep the specification general, such as 'modern high-performance storage', to let bidders propose freely

Key: C.  A functional, standards-based, brand-neutral specification enables fair competition and correct fit. Brand names, copied brochures or vague terms weaken the evaluation.

W-24  Sub-competency 3.1 | Application | Difficult | JD: M27, M11, T26

The Desk manages capacity for a shared government hosting platform. Utilization is now 55% of installed capacity and is growing by 2.5 percentage points each month as institutions are onboarded. Operating policy says utilization must not exceed 80%. New capacity takes 6 months to deliver from the start of procurement. By which month, counted from now, must procurement start at the latest?

A.	Month 2

B.	Month 4

C.	Month 6

D.	Month 10

Key: B.  Utilization reaches 80% after (80 - 55) / 2.5 = 10 months. With a 6-month delivery time, procurement must start no later than month 10 - 6 = 4.

W-25  Sub-competency 3.1 | Analysis | Difficult | JD: T27, T20, M56

Six institutions each need 20 server units at their own peak, but their peaks fall in different months and the combined peak is 55 units. Proposal 1: each institution buys and runs its own 20 units (120 units in total, average utilization about 35%). Proposal 2: one shared pool of 65 units is built and managed centrally. Which conclusion is best supported?

A.	Proposal 1 is better because each institution keeps control and no shared arrangements are needed

B.	Proposal 2 is better because it needs no management arrangements once the units are installed

C.	The proposals are equivalent, since both give each institution at least 20 units at its peak

D.	Proposal 2 meets the combined demand with fewer units and higher utilization, but it requires governance, security isolation and service-level arrangements

Key: D.  The shared pool needs 65 units instead of 120 and achieves higher utilization because peaks do not coincide. Sharing does, however, require governance, isolation and service levels.

W-26  Sub-competency 3.1 | Evaluation | Difficult | JD: M47

Three bids are received for a backup solution. Bid X has the lowest price but does not meet the required recovery time. Bid Y meets all mandatory specifications at a mid-range price. Bid Z exceeds the specifications at the highest price and has unproven local support. Which technical recommendation is best justified?

A.	Recommend Bid Y, because it meets all mandatory requirements at a reasonable price, while X fails a mandatory requirement and Z's extra capability is not required and its support is unproven

B.	Recommend Bid X, because the lowest price gives the best value for public money

C.	Recommend Bid Z, because higher capability will protect the Ministry against future needs

D.	Recommend rejecting all bids and starting again, since none is perfect

Key: A.  Technical evaluation first eliminates bids that fail mandatory requirements, then compares compliant bids on price and risk. Y is compliant at a reasonable price; X fails; Z adds cost for unneeded capability with unproven support.

W-27  Sub-competency 4.1 | Remembering | Easy | JD: T10, T41

Which of the following is a work-management tool that can be used to track the Desk's tasks, milestones and progress?

A.	A network firewall appliance

B.	A server virtualization hypervisor

C.	A project or task-management information system

D.	A tape backup library

Key: C.  Project or task-management systems track tasks, milestones and progress. The other items are infrastructure components, not work-management tools.

W-28  Sub-competency 4.1 | Understanding | Easy | JD: T10

How does using a shared digital tracking system improve the Desk's operations?

A.	It replaces the need for annual and operational plans because progress is recorded automatically

B.	It makes activities more traceable and decisions more data-driven because progress information is recorded in one place

C.	It removes the need for staff to report on their work because the system collects everything

D.	It guarantees that targets are met because deviations are prevented by the system

Key: B.  Recording progress in one shared system improves traceability and data-driven management. It does not replace planning or reporting, and it cannot guarantee results.

W-29  Sub-competency 4.1 | Application | Moderate | JD: T3, T10

The Desk must prepare a quarterly performance report from data supplied monthly by ten project coordinators. Which approach best applies digital tools?

A.	Ask each coordinator to email a summary in their own format and compile the reports manually

B.	Collect progress verbally in monthly meetings and write the report from memory of the discussions

C.	Collect all data at year-end and prepare one consolidated report

D.	Use a standard reporting template in a shared system with defined indicators, so that data is entered directly and aggregated automatically

Key: D.  Standard templates in a shared system improve consistency, timeliness and traceability while reducing manual compilation errors.

W-30  Sub-competency 4.1 | Analysis | Moderate | JD: T21, T22, M66

The Desk's infrastructure inventory lists 40 installed facilities. Utilization data exists for only 25 of them, and 20 of those 25 show utilization below 30%. Which conclusion is most valid?

A.	Most recorded facilities (20 of 25, or 80%) are underutilized, but the 15 without data must be assessed before drawing a conclusion for all 40

B.	Half of all 40 facilities are underutilized, because 20 of 40 fall below 30%

C.	All 40 facilities are underutilized, because the missing data will probably resemble the recorded data

D.	No conclusion can be drawn at all, because the data is incomplete

Key: A.  Only 25 facilities have data, and 20 of 25 (80%) of those are underutilized. The remaining 15 must be assessed before generalizing, but the available data is still informative.

W-31  Sub-competency 4.1 | Creation | Difficult | JD: T41, T10, M66

Which design is best for a Desk information system that will support infrastructure planning, monitoring and decision-making?

A.	Separate spreadsheets kept by each professional, combined manually when management requests information

B.	A public website listing all infrastructure projects, with unrestricted editing rights for all institutions

C.	A central register with a defined data model (site, capacity, utilization, status, linked project, owner, update date), standard data-entry procedures, data-quality checks, role-based access and dashboards

D.	A financial ledger that records the budget spent on each project but no technical or utilization data

Key: C.  A good design has a defined data model, standard procedures, quality controls, controlled access and outputs that serve decisions. It must hold technical and utilization data, not only budget data.

## Key distribution (Work items)

A: 8   B: 7   C: 8   D: 8

# 6. People domain items (38)

Reference codes: T = number in the JD major duties table; M = number in the JD main duties list. Each item shows its key and rationale for reviewers; remove these lines for the exam version.

P-01  Sub-competency 5.1 | Remembering | Easy | JD: M26, M31

Which term describes the maximum amount of data loss, measured in time, that an organization can accept after a disaster?

A.	Recovery time objective (RTO)

B.	Mean time between failures (MTBF)

C.	Recovery point objective (RPO)

D.	Service-level agreement (SLA)

Key: C.  RPO is the maximum tolerable data loss measured in time. RTO is the maximum tolerable downtime, MTBF measures reliability, and an SLA is a contractual service commitment.

P-02  Sub-competency 5.1 | Understanding | Easy | JD: M6, M26

What is the main benefit of server virtualization in a government data center?

A.	Several virtual servers can share the same physical hardware, which improves resource utilization and flexibility

B.	It removes the need for backup and disaster-recovery arrangements

C.	It guarantees that hosted applications never fail

D.	It makes physical servers unnecessary

Key: A.  Virtualization allows multiple virtual servers to share physical hardware, raising utilization and flexibility. It does not remove the need for physical servers, backup or disaster recovery, and it does not guarantee availability.

P-03  Sub-competency 5.1 | Understanding | Moderate | JD: M10, M29

Which statement correctly distinguishes the IaaS and SaaS cloud service models?

A.	IaaS provides a ready-to-use application managed by the provider, while SaaS provides raw computing resources

B.	IaaS is used only for storage, while SaaS is used only for networking

C.	IaaS is always hosted on the customer's own premises, while SaaS is always hosted publicly

D.	IaaS provides virtualized computing, storage and network resources on which the customer installs and manages its own software, while SaaS provides a ready-to-use application managed by the provider

Key: D.  IaaS delivers infrastructure resources that the customer configures; SaaS delivers a finished application. The other statements reverse or misstate the models.

P-04  Sub-competency 5.1 | Application | Moderate | JD: M31, T29

A ministry's citizen-facing service must stay available even if its main data center is lost. The tolerated downtime is about four hours and the budget is limited. Which disaster-recovery arrangement is most appropriate?

A.	Daily backups stored in the same building as the main servers

B.	A secondary site with regularly replicated data, able to be brought into service within the tolerated downtime

C.	A duplicate server placed in another room of the same building

D.	Manual reconstruction of the service from paper records if a disaster occurs

Key: B.  Protection against loss of a whole site requires a separate site with replicated data that can meet the recovery time. Backups or duplicates in the same building are lost with the site, and manual reconstruction cannot meet a four-hour limit.

P-05  Sub-competency 5.1 | Application | Difficult | JD: M31, M26, T29

A system is backed up every 24 hours and takes 6 hours to restore from backup. Its owner states that the service can tolerate at most 1 hour of data loss and 2 hours of downtime. Which recommendation is best justified?

A.	Keep the current arrangement, because daily backups with a 6-hour restore satisfy the objectives

B.	Shorten only the backup interval to 1 hour, since restore time does not affect the requirement

C.	Introduce replication or hourly backups and a standby capability that can restore within 2 hours, because both objectives are currently missed

D.	Extend the retention period of the daily backups, since this reduces both data loss and downtime

Key: C.  A 24-hour backup interval exceeds the 1-hour RPO and a 6-hour restore exceeds the 2-hour RTO, so both must be addressed. Retention length affects neither objective.

P-06  Sub-competency 5.1 | Analysis | Moderate | JD: M27, M28, T26

A shared government hosting platform shows 62% processor utilization but 95% storage utilization, and storage demand is growing. Which analysis is most accurate?

A.	Storage is the constraining resource, so expansion planning should prioritize storage capacity rather than processing capacity

B.	Processing is the constraining resource because processor utilization is above 50%

C.	The platform is balanced, so both resources should be expanded equally

D.	Utilization figures cannot guide capacity planning unless the equipment vendor is known

Key: A.  Capacity is limited by the resource nearest exhaustion. At 95% and growing, storage will constrain the platform first.

P-07  Sub-competency 5.1 | Analysis | Difficult | JD: M30, M29

An institution proposes to place its citizen-records database in a foreign public-cloud region because it is cheaper. Assume national rules require citizens' personal data to remain under national jurisdiction. Which analysis is most sound?

A.	The proposal is acceptable, because lower cost is the decisive criterion when spending public money

B.	The proposal is acceptable if the data is encrypted, since encryption removes all jurisdiction concerns

C.	The proposal should be rejected without analysis, because public cloud is never suitable for any government workload

D.	Lower cost does not resolve the data-sovereignty requirement; the proposal should be assessed against the legal residency rules, and local, government or compliant hosting options should be considered

Key: D.  Infrastructure options must be evaluated on several criteria, including data sovereignty, not on cost alone. Encryption does not remove legal jurisdiction issues, and blanket rejection ignores workloads where cloud is suitable.

P-08  Sub-competency 5.2 | Remembering | Easy | JD: M44, T29

Which term describes a component whose failure would stop an entire service because no alternative exists?

A.	Load balancer

B.	Single point of failure

C.	Redundant path

D.	Failover cluster

Key: B.  A single point of failure has no backup, so its failure stops the service. The other terms describe components or designs used to avoid this.

P-09  Sub-competency 5.2 | Understanding | Easy | JD: M36, M38

Why is redundancy included in the design of network infrastructure for critical government services?

A.	So that the failure of one link or component does not interrupt the critical services

B.	So that the network can be operated without monitoring

C.	So that fewer staff are needed to manage the network

D.	So that the same equipment can be used by all institutions

Key: A.  Redundancy provides alternative paths or components so that one failure does not cause an outage. It does not remove the need for monitoring or management.

P-10  Sub-competency 5.2 | Application | Moderate | JD: M34, M36, M38

A regional government office reaches a shared data center through one leased line from one provider, and its digital services must be continuously available. Which improvement most effectively reduces the risk of disconnection?

A.	Increase the bandwidth of the existing line

B.	Add a second line from the same provider along the same physical route

C.	Add a second connection through a different provider or physical route, with automatic failover

D.	Obtain a written assurance from the provider that outages will not occur

Key: C.  Resilience requires an independent path. More bandwidth does not remove the single point of failure, a line on the same route can fail with the first, and assurances do not prevent outages.

P-11  Sub-competency 5.2 | Application | Moderate | JD: M41, M39

The Desk is setting access-control requirements for a shared government infrastructure platform. Which approach best applies the principle of least privilege?

A.	Give all administrators full administrative rights so that work is never delayed

B.	Use one shared administrator account so that the team's activity is easy to coordinate

C.	Grant permanent broad rights to senior staff because of their seniority

D.	Give each administrator only the access rights needed for their role, review the rights periodically, and remove them when duties change

Key: D.  Least privilege limits each user to what the role requires, with periodic review and removal. Shared accounts and blanket rights weaken accountability and security.

P-12  Sub-competency 5.2 | Application | Difficult | JD: M28, M36, T26

A critical service must achieve 99.9% availability over a year of 8,760 hours. During the year it had outages of 3, 2.5, 4 and 1 hours. Which conclusion is correct?

A.	Met: allowed downtime is about 87.6 hours, and only 10.5 hours occurred

B.	Not met: allowed downtime is about 8.76 hours, but 10.5 hours occurred

C.	Met: 10.5 hours is only about 0.12% of the year, which rounds to 0.1%

D.	Cannot be determined without knowing how many users were affected

Key: B.  Allowed downtime is 0.1% of 8,760 hours = 8.76 hours. Actual downtime was 3 + 2.5 + 4 + 1 = 10.5 hours, which exceeds it (about 99.88% availability), so the target was not met.

P-13  Sub-competency 5.2 | Analysis | Moderate | JD: M37, M38, T26

Monitoring shows a regional link above 90% utilization for four consecutive months with rising traffic, while a nearby link runs at 25%. Which analysis is most appropriate?

A.	No action is needed until the link reaches 100%, since utilization below 100% causes no problems

B.	The nearby link's low utilization shows that the regional link's figures must be wrong

C.	The regional link is a capacity constraint that will degrade services, so expansion or traffic re-engineering should be planned before it saturates

D.	The problem should be handled by reducing the number of monitoring alerts

Key: C.  Sustained high utilization with growth signals an approaching capacity limit; planning must begin before saturation. Ignoring or suppressing the data does not address the constraint.

P-14  Sub-competency 5.2 | Analysis | Difficult | JD: M44, M42, T29

A review of a government data center finds two independent utility power feeds, one generator, a single UPS unit feeding all racks, and two network carriers whose cables enter through one shared duct. Which analysis best identifies the remaining risks?

A.	The single UPS and the shared duct are single points of failure that could still cause an outage despite the redundant power feeds and carriers

B.	No single points of failure remain, because power and network are each supplied from two sources

C.	The generator is the only weakness, since all other components are duplicated

D.	The two carriers are unnecessary, since the shared duct already provides a physical path

Key: A.  Redundancy must extend through the whole chain. One UPS serving all racks and one duct carrying both carriers remain single points of failure.

P-15  Sub-competency 6.1 | Understanding | Easy | JD: T18, M3

What is the main purpose of a government ICT infrastructure needs assessment?

A.	To justify purchases that management has already decided on

B.	To compare the salaries of ICT staff across institutions

C.	To rank vendors according to the size of their earlier contracts

D.	To identify gaps between existing infrastructure and what institutions require, so that priorities can be set on evidence

Key: D.  A needs assessment documents gaps and priorities so that decisions rest on evidence, not on preferences.

P-16  Sub-competency 6.1 | Understanding | Moderate | JD: T11, T13

Which sequence correctly represents the main stages of a research study on government digitalization?

A.	Data collection, problem identification, presentation of findings, analysis, research design

B.	Problem identification, research design, data collection, analysis, presentation of findings and recommendations

C.	Research design, presentation of findings, data collection, problem identification, analysis

D.	Analysis, data collection, research design, recommendations, problem identification

Key: B.  Research proceeds from problem identification through design, data collection and analysis to presentation. The other sequences place later stages before earlier ones.

P-17  Sub-competency 6.1 | Application | Moderate | JD: T12, T21, T22

You must find out why network equipment installed in 20 regional offices is barely used. Which data-collection approach fits best?

A.	Rely only on the equipment vendor's statement about capacity

B.	Combine utilization data from the equipment with structured interviews or surveys of office staff on barriers such as skills, power and applications

C.	Survey only headquarters managers who oversaw the purchase

D.	Count the number of devices installed in each office

Key: B.  Understanding causes of underutilization needs both quantitative usage data and the views of the people at the sites. Vendor claims, distant managers or device counts do not explain use.

P-18  Sub-competency 6.1 | Application | Difficult | JD: T15, T16, M5

A study of another country's national data-center model shows that it works well there. The Desk is asked whether to adopt it. What is the best approach?

A.	Adopt the model fully, since success elsewhere proves it will succeed here

B.	Reject the model, because practices from other countries are never applicable

C.	Adopt only the equipment used in that country and ignore its governance arrangements

D.	Compare the model's operating conditions (scale, funding, governance, connectivity, skills) with the Ethiopian government context, adapt the elements that fit, and pilot before scaling

Key: D.  The JD requires good practices to be adapted to the Ethiopian context rather than adopted without assessment. Benchmarking compares conditions, adapts and pilots.

P-19  Sub-competency 6.1 | Analysis | Moderate | JD: T11, T12, M60

A survey of 50 institutions finds that 30 report unreliable connectivity, but 45 of the 50 responses came from institutions in the capital city. Which conclusion is best supported?

A.	Connectivity problems are reported widely, but the sample is heavily biased toward the capital, so regional conditions are not adequately represented

B.	Sixty percent of all government institutions nationwide have unreliable connectivity

C.	The survey shows that connectivity problems exist only in the capital

D.	The survey is useless because institutions cannot be surveyed reliably

Key: A.  The sample is not representative, so the 60% figure cannot be generalized, and regional conditions remain unknown. The data still carries some information.

P-20  Sub-competency 6.1 | Analysis | Moderate | JD: T14, T16, M72

Two studies on cloud adoption conflict. Study 1 is vendor-funded, covers 8 institutions and describes no method; it reports large savings. Study 2 is by a university, covers 40 institutions and describes its method and cost basis; it reports modest savings with hidden migration costs. Which analysis is most reasonable?

A.	Give both studies equal weight because both are studies

B.	Give Study 1 more weight because vendors know the technology best

C.	Give more weight to Study 2 because its sample, method and cost basis are transparent, while treating Study 1's savings claim with caution

D.	Discard both studies because they conflict

Key: C.  Evidence should be weighed by independence, sample size and transparency of method. Study 2 is stronger on all three.

P-21  Sub-competency 6.1 | Evaluation | Difficult | JD: T16, M72

Which draft recommendation in a research report is best supported and most useful for decision-makers?

A.	Improve government ICT infrastructure in all institutions as soon as possible

B.	Consider adopting emerging technologies where appropriate

C.	Buy new servers for institutions because technology is developing quickly

D.	Establish a shared hosting platform for the 12 institutions with the highest hosting costs, phased over two years; the assessment found that 8 of them use under 30% of their server capacity and 5 lack resilient facilities

Key: D.  A strong recommendation is specific, evidence-based, scoped and actionable. The others are vague or lack supporting evidence.

P-22  Sub-competency 6.2 | Understanding | Easy | JD: T28, M20

What does interoperability between government infrastructure platforms mean?

A.	The ability of a system to handle more users without slowing down

B.	The ability of different systems and platforms to exchange and use data and work together

C.	The use of equipment from a single vendor in all institutions

D.	The ability of a system to recover quickly after a failure

Key: B.  Interoperability is the ability of different systems to exchange data and work together. The other options describe scalability, vendor standardization and resilience.

P-23  Sub-competency 6.2 | Application | Moderate | JD: T25, M15, M19

A consultant's design for a shared platform uses a proprietary interface that only the consultant's own products support, while the approved national architecture requires open, documented standards. What should the Desk's review conclude?

A.	The design does not conform to the approved architecture and should be revised to use open, documented standards, or be justified through a formal exception process

B.	The design conforms, because it works reliably with the consultant's own products

C.	The design conforms, provided the consultant offers a discount

D.	The non-conformity is minor and should not be mentioned, to avoid delaying the project

Key: A.  Reviews check designs against approved architecture. Non-conformity must be reported and resolved by revision or a formal exception, regardless of reliability, price or schedule.

P-24  Sub-competency 6.2 | Application | Moderate | JD: T25, M15

When reviewing an institution's infrastructure proposal for compliance, which documents should the Desk use as its main reference?

A.	The institution's own preferences and previous purchases

B.	The product documentation supplied by the vendor

C.	Approved national policies, standards, architectures, specifications and guidelines

D.	Standards used in other countries, whether or not they have been approved nationally

Key: C.  Compliance is judged against approved national requirements. Institutional preferences, vendor documents or unapproved foreign standards are not the reference.

P-25  Sub-competency 6.2 | Application | Difficult | JD: M51, T25

Reviewing a completion report, the Desk finds that a delivered data-center facility meets 18 of 20 acceptance criteria. The two unmet criteria concern backup-power testing and fire-suppression certification. The supplier requests final acceptance and payment. What is the best action?

A.	Recommend full acceptance, because 90% compliance is sufficient

B.	Recommend that acceptance be withheld or made conditional until the two criteria are met and verified, because they relate to resilience and safety

C.	Recommend acceptance and waive the two criteria, since they can be checked next year

D.	Recommend terminating the contract, without first reviewing the reasons for the shortfall

Key: B.  The unmet criteria are critical to resilience and safety, so acceptance should depend on their fulfilment. A percentage of compliance does not offset critical gaps, and termination without review is disproportionate.

P-26  Sub-competency 6.2 | Analysis | Difficult | JD: T28, M20

Two institutions have built separate systems. Institution X stores citizen identifiers in a different format from Institution Y, and neither system exposes documented interfaces. Which analysis best explains why exchanging data is difficult and how to resolve it?

A.	The bandwidth between the institutions is insufficient; upgrading the bandwidth would resolve it

B.	Server capacity is insufficient in both institutions; buying more servers would resolve it

C.	Both institutions lack staff; recruiting more staff would resolve it

D.	Incompatible data formats and missing standard interfaces block exchange; common data standards and documented interfaces would resolve it

Key: D.  The described obstacles are format incompatibility and the absence of standard interfaces, which are resolved by common data standards and documented interfaces, not by more capacity or staff.

P-27  Sub-competency 6.2 | Evaluation | Difficult | JD: M14, M30, T27

Three architectures are proposed for a shared hosting platform. X uses open standards, redundant components and documented interfaces, and costs 15% more than Z. Y is the cheapest but has single points of failure and proprietary interfaces. Z uses open standards at a mid-range cost but has no disaster-recovery capability. The requirements are interoperability, high availability and disaster recovery. Which evaluation is best?

A.	X best satisfies the requirements; its extra cost buys interoperability, resilience and disaster recovery, while Y and Z each fail at least one mandatory requirement

B.	Y is best, because the lowest cost is the main criterion for public spending

C.	Z is best, because it is mid-priced and its missing feature can be added later at no cost

D.	The three are equal, because each is technically able to host applications

Key: A.  An evaluation should test each option against the mandatory requirements first, then compare cost. Only X meets all three requirements.

P-28  Sub-competency 7.1 | Understanding | Easy | JD: M78, M47

What is a conflict of interest in the context of public ICT procurement?

A.	A disagreement between two departments about the budget

B.	A situation in which two bidders offer the same price

C.	A situation in which an official's private interests could improperly influence, or appear to influence, official decisions

D.	A delay caused by a shortage of technical staff

Key: C.  A conflict of interest arises when private interests could, or could appear to, improperly influence official decisions.

P-29  Sub-competency 7.1 | Application | Moderate | JD: M78, M47

A Desk professional on a technical evaluation team discovers that one bidder is owned by his cousin. What should he do?

A.	Continue evaluating, taking care to score all bidders fairly

B.	Say nothing, since a cousin is not a close enough relative to matter

C.	Withdraw from the evaluation without giving any explanation

D.	Declare the relationship to the Desk Leader in writing and withdraw from evaluating that procurement

Key: D.  Conflicts must be declared and the person must step back from the decision. Continuing, staying silent or withdrawing without explanation all weaken transparency and accountability.

P-30  Sub-competency 7.1 | Application | Moderate | JD: M78

A vendor offers the Desk Leader a personal gift of a laptop 'in appreciation' shortly before a technical evaluation of the vendor's proposal. What is the appropriate response?

A.	Accept the gift, since it is not conditional on the result of the evaluation

B.	Decline the gift, report the offer according to institutional procedures, and ensure the vendor is evaluated on merit

C.	Accept the gift after the evaluation is complete, so that it cannot influence the result

D.	Decline the gift but keep the offer confidential to protect the vendor's reputation

Key: B.  Gifts from bidders compromise integrity, and the offer itself should be reported. Accepting later or concealing the offer still undermines transparency.

P-31  Sub-competency 7.1 | Application | Difficult | JD: M78, T41

The Desk holds an assessment dataset that reveals security weaknesses in several institutions' infrastructure. A journalist asks the Desk Leader for the data for a story. What is the most appropriate response?

A.	Provide the full dataset, since all government information is public

B.	Provide it only for the institutions that the Desk Leader considers well managed

C.	Decline informal release, treat the data as sensitive, and refer the request to the authorized channel for releasing information

D.	Provide it if the journalist promises not to name the institutions

Key: C.  Data revealing vulnerabilities is sensitive and must be handled through authorized channels. Selective or informal release, or unenforceable promises, could expose critical systems.

P-32  Sub-competency 7.1 | Analysis | Moderate | JD: M78, M47, M76

A professional under the Desk consistently gives favorable technical ratings to proposals from one supplier, although the ratings are not supported by the evaluation criteria. Which analysis is most accurate?

A.	The pattern suggests bias, possibly a conflict of interest, and should be reviewed against the criteria and addressed through the accountability procedure

B.	The ratings are acceptable, because professionals may use their judgment freely

C.	The pattern is normal, because that supplier is probably technically better

D.	The pattern matters only if the supplier is finally awarded the contract

Key: A.  Ratings must be justified by the evaluation criteria. A consistent, unsupported pattern indicates possible bias and calls for review and accountability.

P-33  Sub-competency 8.1 | Remembering | Easy | JD: T5, M73

Which of the following is a core duty of the Desk Leader towards the staff of the Desk?

A.	Performing all technical tasks personally

B.	Setting clear targets, monitoring performance, and providing feedback and coaching

C.	Approving the salaries of the Desk's staff

D.	Recruiting staff for other Desks in the Ministry

Key: B.  The JD assigns the Desk Leader responsibility for targets, performance monitoring, feedback and coaching.

P-34  Sub-competency 8.1 | Understanding | Moderate | JD: T5, M77

Why should the Desk Leader give staff constructive feedback during the performance period, not only at year-end?

A.	It replaces the need for a formal performance evaluation

B.	Its main purpose is to document shortcomings for later disciplinary action

C.	It reduces the need to set individual targets

D.	It allows problems to be corrected early and supports continuous improvement of performance

Key: D.  Ongoing feedback allows early correction and improvement. It complements, and does not replace, formal evaluation or target setting.

P-35  Sub-competency 8.1 | Understanding | Moderate | JD: T6, M79

How does identifying staff competency gaps benefit the Desk?

A.	It provides grounds for reducing the number of staff

B.	It allows the leader to avoid assigning difficult tasks to staff

C.	It guides targeted capacity-building so that technical and managerial capacity is strengthened where it is needed

D.	It ensures that all staff receive identical training

Key: C.  Identifying gaps directs capacity-building to real needs, which is the purpose stated in the JD.

P-36  Sub-competency 8.1 | Application | Moderate | JD: M73, M75, T5

A professional with strong networking skills but limited research experience is to lead a study of connectivity gaps in 20 regional offices. What is the best approach for the Desk Leader?

A.	Assign the task with clear expectations and quality checkpoints, pair the professional with an experienced researcher, and provide coaching

B.	Assign the task without support, to see whether the professional can manage

C.	Take over the task personally so that the professional never faces difficulty

D.	Assign the task to the most senior professional regardless of skills, so that no one needs development

Key: A.  Effective delegation combines clear expectations, checkpoints and coaching, which build capacity while protecting quality.

P-37  Sub-competency 8.1 | Analysis | Moderate | JD: T4, T5, M76

Team outputs are frequently late. The Desk Leader notes that targets were communicated only orally, no written deadlines exist, and two staff members have not attended relevant training. Which analysis is most accurate?

A.	The delays are due to poor motivation, so warnings should be issued to all staff

B.	The delays are due to inadequate technology, so new equipment should be purchased

C.	The delays are normal for technical work and require no action

D.	The delays likely arise from unclear written targets and deadlines and possible skill gaps, so the leader should clarify targets and address capacity needs

Key: D.  The evidence points to unclear targets and skill gaps, which the leader can correct. The other explanations are not supported by the facts.

P-38  Sub-competency 8.1 | Creation | Difficult | JD: T6, M67, M68

Which is the best-designed approach for building the capacity of the Desk's professionals in cloud and data-center management over the year?

A.	Send all staff to the same external training once, in the last month of the year

B.	Assess individual competency gaps, set a development plan linking training, on-the-job assignments and knowledge-sharing sessions to those gaps, and evaluate results against performance targets

C.	Leave staff to learn independently, and reward those who volunteer

D.	Recruit new specialists and stop developing existing staff

Key: B.  A sound design starts from assessed gaps, combines several learning methods and measures results. One-off training, self-study only or replacing staff do not build sustained capacity.

## Key distribution (People items)

A: 9   B: 10   C: 9   D: 10

# 7. Results domain items (51)

Reference codes: T = number in the JD major duties table; M = number in the JD main duties list. Each item shows its key and rationale for reviewers; remove these lines for the exam version.

R-01  Sub-competency 9.1 | Understanding | Moderate | JD: M30, T16

Why should the Desk evaluate infrastructure options against several criteria (such as cost, performance, scalability, availability, security, data sovereignty, interoperability and sustainability) rather than against cost alone?

A.	Because using more criteria always produces a lower total cost

B.	Because cost is not relevant to decisions about public infrastructure

C.	Because the number of criteria used matters more than how important each criterion is

D.	Because the cheapest option may fail requirements that determine whether the infrastructure can support government services reliably and lawfully over time

Key: D.  Options must be judged on all factors that determine fitness for purpose. A low-cost option that fails availability, security or sovereignty requirements is not a good decision.

R-02  Sub-competency 9.1 | Application | Moderate | JD: M30, M29, T16

The Desk must recommend whether a new national service that handles sensitive data, needs high availability and expects variable demand should be hosted on a shared government cloud or on dedicated servers in the owner institution. Which is the most appropriate way to compare the two options?

A.	Choose the option that the owner institution prefers, since it will operate the service

B.	Score both options against agreed criteria (cost, availability, security, scalability, sovereignty, operations) weighted by the service's needs, and recommend the better-scoring option with reasons

C.	Choose the option with the lowest purchase price

D.	Choose the option that is used by most other countries

Key: B.  A transparent, criteria-based comparison weighted by the service's needs gives an evidence-based recommendation. Preference, price alone or popularity elsewhere do not.

R-03  Sub-competency 9.1 | Application | Difficult | JD: M30, T16

Eight institutions need hosting. Option 1: each builds its own dedicated servers at a five-year cost of 1.5 million birr per institution. Option 2: a shared platform with an initial investment of 6 million birr plus 0.5 million birr operating cost per year, for all eight together, over five years. Assume both options meet all requirements. Which conclusion about five-year cost is correct?

A.	Option 2 costs 8.5 million birr against 12 million for Option 1, so the shared platform is cheaper by 3.5 million birr

B.	Option 1 costs 8.5 million birr against 12 million for Option 2, so the dedicated servers are cheaper by 3.5 million birr

C.	Option 2 costs 6.5 million birr against 12 million for Option 1, so the shared platform is cheaper by 5.5 million birr

D.	The options cannot be compared because they are funded in different ways

Key: A.  Option 1: 8 x 1.5 = 12 million. Option 2: 6 + (0.5 x 5) = 8.5 million. Operating costs must be counted for all five years, and options with different funding can still be compared on total cost.

R-04  Sub-competency 9.1 | Analysis | Moderate | JD: M30, T16, T27

Three options are proposed for a ministry system. Requirements: data sovereignty is mandatory and availability must be at least 99.5%. Local government cloud: meets sovereignty, moderate cost, 99.5% availability. Foreign public cloud: lowest cost, 99.99% availability, does not meet sovereignty. On-premises dedicated servers: highest cost, 99.9% availability, meets sovereignty. Which analysis is most accurate?

A.	The foreign public cloud is best because it has the lowest cost and the highest availability

B.	All three options are equally suitable because each has availability above 99%

C.	The foreign public cloud is eliminated by the mandatory sovereignty requirement; the choice is between the other two on cost and availability, and the local government cloud meets all requirements at lower cost

D.	The on-premises option is best because its higher cost indicates higher quality

Key: C.  Mandatory requirements act as a filter before options are compared. The foreign cloud fails sovereignty; of the remaining two, the local cloud meets the availability minimum at lower cost.

R-05  Sub-competency 9.1 | Analysis | Difficult | JD: T16, T26, M27

A concept note recommends building a new data center because existing government data centers are 'full'. Assessment data show that three data centers have 90% of their rack space occupied, but average power and processing utilization is 35%, and only 20% of workloads are virtualized. Which analysis is most sound?

A.	The recommendation is sound because 90% space occupancy shows that no capacity is left

B.	The evidence suggests that space is used inefficiently, so consolidation and virtualization should be evaluated before investing in a new data center

C.	The recommendation is sound only if the new data center is larger than the existing ones

D.	The utilization data are irrelevant because only rack space determines capacity

Key: B.  Occupied space is not the same as used capacity. Low utilization and limited virtualization show that existing capacity could be used more efficiently before new investment.

R-06  Sub-competency 9.1 | Evaluation | Difficult | JD: T16, M72

An institution's proposal to move to a shared cloud claims that 'cloud is cheaper'. Its cost analysis compares five years of cloud cost with one year of on-premises cost, and excludes migration, staff training and connectivity costs. Which evaluation is most accurate?

A.	The conclusion is reliable because cloud is generally cheaper

B.	The conclusion is reliable as long as the cloud provider has a good reputation

C.	The conclusion is unreliable only because migration to cloud is never worth doing

D.	The cost conclusion is unreliable because it compares different periods and omits major cost elements; the analysis should be redone on a like-for-like basis

Key: D.  A valid cost comparison uses the same period and all relevant costs. The proposal fails on both counts, so its conclusion cannot support a decision.

R-07  Sub-competency 9.1 | Creation | Difficult | JD: T16, M45

Which is the best-designed structure for a concept note asking management to approve expansion of a regional connectivity program?

A.	Problem and evidence of need, objectives, options considered, recommended option, costs and resources, risks and mitigation, implementation plan with milestones, and expected results with indicators

B.	Executive summary, vendor profiles, equipment list and price quotations

C.	History of the Ministry, general benefits of connectivity and a request for budget

D.	Technical diagrams and a list of the Desk's previous projects

Key: A.  A decision-ready concept note links evidence to options, cost, risk, implementation and expected results. The alternatives lack the elements management needs to decide.

R-08  Sub-competency 9.2 | Understanding | Easy | JD: M42

What is risk mitigation in infrastructure management?

A.	Ignoring risks that have not yet occurred

B.	Transferring all responsibility for risks to the supplier

C.	Actions taken to reduce the likelihood or the impact of an identified risk

D.	Recording a risk in a register and taking no further action

Key: C.  Mitigation means acting to reduce the likelihood or impact of a risk. Recording without action, ignoring, or handing over all responsibility are not mitigation.

R-09  Sub-competency 9.2 | Application | Moderate | JD: M44, T29

A risk review finds that a critical government platform runs on a single database server with no standby. Which mitigation is most appropriate?

A.	Add a standby database server with replication and tested failover, and include it in the continuity plan

B.	Buy a second server and keep it switched off in storage

C.	Document the risk and accept it, since no failure has occurred so far

D.	Increase the number of staff who monitor the server

Key: A.  A standby with replication and tested failover removes the single point of failure. An unconfigured spare, acceptance of the risk or more monitoring does not keep the service running.

R-10  Sub-competency 9.2 | Application | Moderate | JD: M42, M43

The Desk's risk register shows: R1, high likelihood, low impact; R2, low likelihood, very high impact on critical services; R3, medium likelihood, high impact; R4, low likelihood, low impact. Resources allow only two risks to be treated first. Which selection is most appropriate?

A.	R1 and R4, because they are the easiest to resolve

B.	R1 and R3, because high-likelihood risks are always treated before high-impact ones

C.	R4 only, because low-impact risks are the safest to treat

D.	R2 and R3, because they carry the greatest potential impact on critical services

Key: D.  Prioritization combines likelihood and impact, giving priority to risks that could seriously harm critical services. Ease of treatment or likelihood alone is not sufficient.

R-11  Sub-competency 9.2 | Application | Difficult | JD: T42, M43

A data-center project has a fixed budget with a 5% contingency. A risk assessment finds that the planned single cooling system is a single point of failure whose failure would be very costly. Adding redundancy would cost 8% more. What is the best decision?

A.	Keep the single cooling system and accept the risk in order to stay within budget

B.	Cancel the project until a larger budget is approved

C.	Recommend adding cooling redundancy, seek approval for the extra 3% through reallocation or a budget adjustment, and document the risk-based justification

D.	Add the redundancy and use the whole contingency without informing management, since 5% is close to 8%

Key: C.  The redundancy is justified by the risk, and the shortfall is 8% - 5% = 3%, which must be approved openly. Accepting a critical risk, cancelling or acting without approval are all weaker.

R-12  Sub-competency 9.2 | Analysis | Moderate | JD: M42, M50, T2

Three consecutive monthly reports show that the Desk's planned infrastructure assessments missed their targets, and each report gives the same reason: 'lack of transport to regional offices'. Which analysis is most useful for decision-making?

A.	The delays are random and need no corrective action

B.	The recurring cause points to a resource constraint that needs corrective action, such as arranging transport or rescheduling the visits, rather than repeating the same explanation each month

C.	The delays are caused by unwilling staff, so all staff should be reprimanded

D.	The target should be removed from the plan once it has been missed for the first time

Key: B.  A repeated cause is a systemic constraint. Monitoring exists to trigger corrective action, not to repeat explanations.

R-13  Sub-competency 9.2 | Analysis | Difficult | JD: T27, M42, T29

A ministry plans to consolidate the server rooms of 15 institutions into one national data center to reduce cost and improve security. Which analysis of the resulting risks is most accurate?

A.	Consolidation removes all infrastructure risks because the equipment is in one professionally managed place

B.	Consolidation increases every risk and should therefore not be pursued

C.	Consolidation changes only the cost, not the level of risk

D.	Consolidation reduces some risks (fragmented security, poor facilities) but concentrates others: failure of the single site or its links could affect all 15 institutions, so a recovery site, redundant links and phased migration should be planned

Key: D.  Consolidation changes the risk profile: it reduces some risks and concentrates others. A sound plan adds recovery capability, redundancy and phasing.

R-14  Sub-competency 10.1 | Remembering | Easy | JD: M49, T2

Which four parameters does the Desk track when monitoring an infrastructure project against its approved baseline?

A.	Scope, schedule, budget and quality

B.	Vendor, brand, model and price

C.	Staff, salary, location and equipment

D.	Risk, reputation, revenue and reporting

Key: A.  The JD requires projects to be monitored against approved scope, schedule, budget, quality, technical specifications and expected results.

R-15  Sub-competency 10.1 | Understanding | Easy | JD: M62

What is the purpose of a milestone in project monitoring?

A.	It is a final report submitted after the project closes

B.	It marks a significant point in the plan against which progress is checked, so that delays can be detected early

C.	It is a budget line approved by the finance unit

D.	It is a meeting to introduce vendors to the Desk

Key: B.  Milestones are checkpoints in the plan that allow progress to be measured and delays to be detected early.

R-16  Sub-competency 10.1 | Understanding | Moderate | JD: T40, T42

Which statement best describes the difference between monitoring and evaluation?

A.	Monitoring assesses whether results were achieved; evaluation tracks implementation against the plan

B.	Monitoring is done only by external auditors; evaluation is done only by the Desk

C.	Monitoring is the continuous tracking of implementation against the plan; evaluation assesses whether results and objectives were achieved and why

D.	They are the same activity carried out at different times

Key: C.  Monitoring tracks progress during implementation; evaluation judges results and their causes.

R-17  Sub-competency 10.1 | Application | Moderate | JD: M50, T2

A monitoring report shows that a regional data-center project is two months behind schedule because equipment delivery is delayed. The supplier promises delivery in four more weeks. What is the most appropriate response?

A.	Wait for the delivery without action, since the delay is the supplier's responsibility

B.	Cancel the contract immediately and restart procurement

C.	Update the schedule, assess the effect on dependent activities, follow up formally with the supplier for a firm delivery date, and report the deviation and revised plan to management

D.	Leave the delay out of the report so that management is not worried

Key: C.  Monitoring must lead to corrective action and transparent reporting. Doing nothing, cancelling without analysis or hiding the delay all fail this.

R-18  Sub-competency 10.1 | Application | Moderate | JD: M49, M50

A project plan required 50% of the work to be complete by the end of month 6, with 5 million birr of planned spending by then. At the end of month 6, 50% of the work is complete and 6.5 million birr has been spent. What does this indicate?

A.	The project is on budget and on schedule

B.	The project is on schedule but over budget

C.	The project is under budget but behind schedule

D.	The project is over budget and behind schedule

Key: B.  Work completed (50%) equals the planned 50%, so the project is on schedule. Spending of 6.5 million against a planned 5 million is 1.5 million (30%) over budget.

R-19  Sub-competency 10.1 | Application | Difficult | JD: M63, T2

Monthly reports show that three parallel infrastructure projects are each waiting for the same institution to approve network access, causing delays of 6, 5 and 7 weeks. Which response is best?

A.	Record each delay separately in each project's report, without further action

B.	Ask each project team to work around the approval by proceeding without it

C.	Extend the deadlines of all three projects by 7 weeks without further analysis

D.	Recognize a common bottleneck, escalate it to the appropriate management level with the impact data, agree a timeline with that institution, and re-sequence work in the meantime

Key: D.  A shared cause is a bottleneck that must be resolved at the right level, with data on its impact. Treating delays separately, bypassing approvals or extending deadlines automatically do not resolve it.

R-20  Sub-competency 10.1 | Analysis | Moderate | JD: M49, T42

A project report shows that 90% of the budget has been spent and 60% of the physical work is complete, with the end date unchanged. Which analysis is most accurate?

A.	The project is likely to exceed its budget or fail to complete its scope by the end date, so corrective action is needed now

B.	The project is on track because the end date has not changed

C.	The project is ahead of schedule because 90% of the budget has been used

D.	The figures cannot be interpreted without knowing the supplier

Key: A.  Spending is running well ahead of progress (90% vs 60%). Without correction, the budget will be exceeded or the scope will not be completed.

R-21  Sub-competency 10.2 | Remembering | Easy | JD: M28, T21

Which indicator expresses the percentage of time that a service is operational and accessible during a given period?

A.	Availability

B.	Latency

C.	Throughput

D.	Storage capacity

Key: A.  Availability is the share of time a service is operational. Latency is delay, throughput is the volume processed, and capacity is the maximum that can be supported.

R-22  Sub-competency 10.2 | Understanding | Easy | JD: T21, T22

What does a low utilization rate of a government server room indicate, taken by itself?

A.	That the equipment is faulty

B.	That the server room should be closed immediately

C.	That installed capacity is used only in part, so the reasons (demand, skills, applications, access) should be investigated

D.	That the institution is performing well

Key: C.  Low utilization is a signal to investigate. It does not by itself show a fault, justify closure or indicate good performance.

R-23  Sub-competency 10.2 | Understanding | Moderate | JD: M28, T21

Why does the Desk track capacity and utilization together with availability?

A.	Because availability cannot be reported unless utilization is reported

B.	Because utilization is relevant only to private-sector infrastructure

C.	Because capacity indicators replace the need for availability targets

D.	Availability shows whether services are running, while capacity and utilization show whether the infrastructure can support current and future demand and is being used effectively

Key: D.  The indicators answer different questions: is the service running, is there enough capacity, and is it being used? All are needed to manage infrastructure.

R-24  Sub-competency 10.2 | Application | Moderate | JD: T24, T40

Which indicator is most suitable for monitoring how equitably government ICT infrastructure is accessible across regions?

A.	Total number of servers purchased by the Ministry

B.	Percentage of regional government offices with connectivity and hosting access, reported by region and compared with federal offices

C.	Number of workshops held at Ministry headquarters

D.	Average age of the Desk's staff

Key: B.  Equity of access is measured by comparing coverage across regions and institution types. The other options do not describe access.

R-25  Sub-competency 10.2 | Application | Difficult | JD: T22, M66

The Desk flags a facility as underutilized if its utilization was below 30% in each of three consecutive months. Monthly utilization was: F1: 25%, 28%, 27%; F2: 20%, 35%, 22%; F3: 15%, 18%, 29%; F4: 28%, 30%, 25%. Which facilities are flagged?

A.	F1 only

B.	F1 and F3

C.	F1, F3 and F4

D.	All four facilities

Key: B.  F1 (25, 28, 27) and F3 (15, 18, 29) were below 30% in all three months. F2 had 35% in month 2, and F4 had exactly 30% in month 2, which is not below 30%.

R-26  Sub-competency 10.2 | Analysis | Moderate | JD: M28, T21

A shared hosting platform reports 99.95% availability, yet institutions complain of frequent service interruptions. Which analysis is most appropriate?

A.	The complaints must be wrong, because the platform figure is above 99.9%

B.	The availability figure must be wrong, because any complaint proves a fault

C.	The complaints should be ignored because they are subjective

D.	Platform-level availability may hide outages of specific services, links or sites, so availability should be analyzed at service and site level and its measurement checked

Key: D.  An aggregate figure can conceal problems at service or site level. Both the data and the complaints deserve analysis.

R-27  Sub-competency 10.2 | Analysis | Difficult | JD: T22, T21

Ten institutions were allocated hosting capacity. Three use over 80% of their allocation, and seven use less than 10%. A user survey shows that the seven lack application-migration skills and reliable network links. Which conclusion is best supported?

A.	Capacity is excessive, so the platform should be scaled down

B.	The three heavy users should be required to share their allocation with the other seven

C.	Low overall utilization results from adoption barriers at the seven institutions, not from excess capacity, so the response should first address those barriers

D.	More capacity should be added, since three institutions already use over 80%

Key: C.  The evidence identifies skills and connectivity barriers as the cause of low use. Changing capacity before removing them would not solve the problem.

R-28  Sub-competency 11.1 | Remembering | Easy | JD: M64, T21

Which review examines a completed infrastructure project to assess whether it achieved its intended results and to identify lessons?

A.	Post-implementation review

B.	Pre-feasibility review

C.	Procurement audit

D.	Daily operations log review

Key: A.  A post-implementation review assesses results and lessons after completion. The other reviews serve different purposes.

R-29  Sub-competency 11.1 | Understanding | Easy | JD: T21, T22

Why does the Desk treat 'infrastructure installed' and 'infrastructure effectively utilized' as different results?

A.	Installation is more important than use because it costs more

B.	Utilization is measured by the supplier and installation by the Desk

C.	Installation is an output; the intended benefit is achieved only when the infrastructure is used for government functions and digital services

D.	They are the same result if the equipment works

Key: C.  The JD stresses that installing infrastructure is an output, while effective utilization is the result that matters.

R-30  Sub-competency 11.1 | Application | Moderate | JD: T40, M64

Which set of indicators best measures whether a new shared hosting platform has achieved its intended results?

A.	Number of institutions migrated, percentage of capacity used, service availability and number of digital services running on the platform

B.	Number of servers delivered, contract value, delivery date and the supplier's name

C.	Number of supplier training sessions, number of meetings and volume of documents produced

D.	Floor area of the facility and number of racks installed

Key: A.  Results indicators measure use and service performance. The other sets measure inputs or outputs.

R-31  Sub-competency 11.1 | Application | Moderate | JD: M64, T21

A post-implementation review of a completed network project must judge whether it achieved its intended results. Which combination of sources is most appropriate?

A.	The supplier's completion certificate and the final invoice

B.	Original project objectives and indicators, actual usage and performance data, user feedback, and cost and schedule records

C.	Photographs of the installed equipment

D.	The project team's own summary of what went well

Key: B.  A review needs objectives, measured results, user views and cost data. Certificates, photographs or self-assessment alone cannot show results.

R-32  Sub-competency 11.1 | Application | Difficult | JD: T21, T40

A network project aimed to connect 60 offices, with 80% of them actively using the link within a year. At review, all 60 offices were connected on time and within budget, but only 30 use the link actively. Which evaluation is correct?

A.	The project was fully successful because all offices were connected on time and within budget

B.	The project failed completely because only half of the offices use the links

C.	The project cannot be evaluated until all 60 offices use the links

D.	The output target was fully achieved, but the utilization outcome (50% against 80%) was not, so the project delivered infrastructure without fully achieving the intended results

Key: D.  30 of 60 offices is 50%, below the 80% target. Delivery (output) was achieved, but the intended result (use) was only partly achieved.

R-33  Sub-competency 11.1 | Analysis | Moderate | JD: T22, M64

An evaluation shows that a regional data center built two years ago runs at 12% utilization. What is the most useful first step in the analysis?

A.	Recommend closing the data center

B.	Recommend building a second data center to attract users

C.	Record the low utilization in the report and take no further step

D.	Identify the barriers to use, such as connectivity, skills, application readiness, awareness or governance, using data and stakeholder input

Key: D.  The cause of low utilization must be understood before deciding on action. Closing, expanding or ignoring do not address the cause.

R-34  Sub-competency 11.1 | Evaluation | Difficult | JD: T21, T22, M64

Two evaluation reports on a completed project are submitted. Report 1 concludes 'Project successful: all equipment delivered and installed, budget respected.' Report 2 confirms delivery and budget, but finds usage of 20% against a 70% target, identifies skills and power-supply barriers, and recommends corrective actions with owners and dates. Which judgment is best?

A.	Report 1 is better, because it gives management a clear and positive message

B.	The reports are equally good, because both confirm delivery and budget

C.	Report 2 is better, because it assesses actual utilization against targets, explains the barriers and recommends corrective action

D.	Neither is appropriate, because evaluations should not be done after installation

Key: C.  Evaluation must go beyond outputs to results and their causes. Report 2 does this; Report 1 stops at delivery.

R-35  Sub-competency 11.2 | Understanding | Moderate | JD: T34

Which statement best explains why the Desk must monitor compliance with approved standards, and not only develop and publish them?

A.	Without monitoring, the Ministry cannot know whether the standards are actually being implemented or where barriers exist

B.	Publication of a standard automatically guarantees compliance

C.	Monitoring is needed only when institutions ask for it

D.	Monitoring compliance is the responsibility of the vendors

Key: A.  The JD states that developing a standard is not enough; the Desk must disseminate it and monitor implementation.

R-36  Sub-competency 11.2 | Understanding | Moderate | JD: T35

Which statement best describes the difference between non-compliance and an implementation barrier?

A.	Non-compliance is a cause that prevents institutions from meeting a requirement; an implementation barrier is failure to meet it

B.	Non-compliance is failure to meet a requirement; an implementation barrier is a cause, such as lack of skills, budget or clarity, that prevents institutions from meeting it

C.	They are the same, and both should lead to sanctions

D.	Barriers apply only to vendors, and non-compliance applies only to institutions

Key: B.  Non-compliance is the finding; barriers are the underlying causes. Distinguishing them allows evidence-based corrective action.

R-37  Sub-competency 11.2 | Application | Moderate | JD: T35, M23

The Desk plans compliance assessments of 40 institutions' server rooms against a national standard. Which approach best applies sound assessment practice?

A.	Use a checklist derived from the standard's measurable requirements, apply it consistently, record evidence for each finding, and classify findings by severity

B.	Rely on each institution's own statement of compliance without verification

C.	Let each assessor use personal judgment about what matters in each institution

D.	Assess only the institutions that have previously complained

Key: A.  A consistent, evidence-based checklist makes results comparable and defensible. Self-declaration, ad hoc judgment or selective coverage weaken the assessment.

R-38  Sub-competency 11.2 | Application | Moderate | JD: T35, M24, T36

An assessment finds that an institution's server room has no fire suppression and no temperature monitoring, both required by the national standard. The institution has no budget available at present. What is the most appropriate recommendation?

A.	Recommend immediate closure of the institution's ICT operations

B.	Record the findings as observations only, since it is the first assessment

C.	Instruct the institution to buy the most expensive available solutions immediately

D.	Document the findings by severity, recommend a time-bound corrective plan that starts with the safety-critical fire suppression, and offer technical guidance on options and costs

Key: D.  Corrective recommendations should be prioritized by severity, time-bound and supported by guidance. Closure, inaction or unrealistic orders do not lead to compliance.

R-39  Sub-competency 11.2 | Analysis | Moderate | JD: T35, M24

An assessment of 10 institutions finds that 6 comply with the access-control requirement, but only 2 comply with the requirement for a documented disaster-recovery plan tested annually. Which analysis is most helpful?

A.	Access control is the main problem because four institutions fail it

B.	The disaster-recovery requirement is the main implementation gap, so the Desk should investigate its causes (clarity, skills, resources) and prioritize guidance and follow-up on it

C.	Both requirements are equal problems because both have some failures

D.	The results show that the disaster-recovery requirement should be removed

Key: B.  Eight of ten institutions fail the disaster-recovery requirement, compared with four for access control. The larger gap deserves priority and cause analysis.

R-40  Sub-competency 11.2 | Analysis | Difficult | JD: T35, T34

Compliance with a standard rose from 30% to 70% in one year after the Desk issued the standard and held orientation sessions. The first-year figure came from a random sample of 40 institutions; the second-year figure came from 10 institutions that volunteered. Which analysis is most accurate?

A.	The rise proves that the orientation sessions caused the improvement

B.	The figures are fully comparable because both are percentages

C.	The rise may be partly real, but the different sampling means the two figures are not directly comparable, so the conclusion is not yet reliable

D.	The figures are worthless because the sample sizes differ

Key: C.  A small, self-selected sample can overstate compliance, so it cannot be compared directly with a random sample. The data still suggest improvement but need a comparable re-assessment.

R-41  Sub-competency 11.2 | Evaluation | Difficult | JD: M24, T35

Which corrective-action plan produced after a compliance assessment is best?

A.	A general list of recommendations stating that institutions should improve compliance

B.	A list of the institutions that failed, with no actions

C.	A commitment letter from each institution promising to comply, with no verification

D.	Findings ranked by severity, each linked to a specific corrective action, owner, deadline and verification method, with follow-up dates and escalation if deadlines are missed

Key: D.  A strong plan is specific, prioritized, assigned, time-bound and verifiable. The alternatives lack actions, ownership or verification.

R-42  Sub-competency 12.1 | Remembering | Easy | JD: T7, T8

Which of the following is an appropriate formal channel for receiving service-user requirements and complaints?

A.	A documented request and complaint-handling procedure with a designated contact point

B.	Informal conversations in corridors with no records

C.	Personal mobile messages between individual staff and users

D.	Notices posted only at Ministry headquarters

Key: A.  Formal, documented channels with a clear contact point allow requirements to be captured, communicated and followed up.

R-43  Sub-competency 12.1 | Understanding | Easy | JD: T8

Why is it important to follow up on responses to service-user complaints and requirements?

A.	To assign blame to the technical teams

B.	To reduce the number of complaints recorded

C.	To confirm that the issues were actually addressed and to improve services and user satisfaction

D.	To avoid receiving further requirements

Key: C.  Follow-up closes the loop: it confirms that issues were resolved and supports improved services and satisfaction.

R-44  Sub-competency 12.1 | Application | Moderate | JD: T8, T7

Several regional institutions report slow connectivity to the Desk, each to a different person at the Ministry. What is the best way to manage these reports?

A.	Ask each institution to contact the service provider directly

B.	Register all reports centrally, forward them to the responsible technical team, track the responses and inform the institutions of progress

C.	Wait until reports accumulate and address them at year-end

D.	Reply to each institution informally and keep no record

Key: B.  Central registration, forwarding, tracking and feedback ensure that reports are addressed and patterns are visible.

R-45  Sub-competency 12.1 | Application | Moderate | JD: T33, T36

A new national infrastructure standard has been approved. Which communication approach best supports its implementation by institutions?

A.	Publish the standard on the Ministry notice board only

B.	Provide the current approved document to all target institutions, hold orientation sessions, and designate a contact point for technical clarification

C.	Send the standard to the institutions' heads with no follow-up

D.	Wait for institutions to ask for the standard

Key: B.  Implementation requires that institutions receive the current document, understand it and can obtain clarification.

R-46  Sub-competency 12.1 | Analysis | Moderate | JD: T8, T7

Complaint data for the year show 60 complaints, of which 42 concern the same issue, an unclear procedure for requesting hosting space, and an average response time of 15 working days against a 5-day target. Which analysis is most useful?

A.	The main issue is the number of complaints, and staff should be reprimanded

B.	Response time is the only issue, since the procedure has no effect on complaints

C.	The main issue is an unclear request procedure (70% of complaints), compounded by slow responses, so clarifying the procedure and shortening response time would address most complaints

D.	The complaints are unrelated to each other and should be handled one by one

Key: C.  42 of 60 complaints (70%) share one cause, and response times miss the target. Fixing these two issues would resolve most complaints.

R-47  Sub-competency 12.2 | Understanding | Moderate | JD: T43, M65

Why should lessons learned from completed infrastructure projects be documented and shared?

A.	To prevent repeated problems and support continuous improvement of future plans and projects

B.	To assign responsibility for problems to individuals

C.	To meet an archiving requirement with no further use

D.	To reduce the need to evaluate future projects

Key: A.  Documenting and sharing lessons builds institutional learning and prevents repeated implementation problems.

R-48  Sub-competency 12.2 | Application | Moderate | JD: T43, M65

After a data-center project, the team records several lessons. Which lesson is best formulated for reuse?

A.	The project was difficult

B.	Communication should be better

C.	The supplier was slow

D.	Delays occurred because site power capacity was not verified before equipment was ordered; future projects should include a site-readiness check before procurement

Key: D.  A reusable lesson states the cause and the specific practice to apply in future. The other statements are too vague to guide action.

R-49  Sub-competency 12.2 | Application | Moderate | JD: T43, M68

Projects in three different regions were delayed because institutions had not prepared their server rooms. How should the Desk use this recurring experience?

A.	Handle each future delay individually as it arises

B.	File the experience in the archive with no other action

C.	Build a site-readiness check into project planning guidelines and share the lesson with institutions and ICT professionals

D.	Ask suppliers to accept the delays as part of their risk

Key: C.  Recurring lessons should be institutionalized in guidelines and shared, so the same problem is prevented instead of repeatedly managed.

R-50  Sub-competency 12.2 | Analysis | Difficult | JD: T42, T43

Reports over three years show recurring low utilization of newly installed infrastructure in different institutions, each time attributed to a different cause: 'lack of training', 'application not ready', 'no budget for connectivity'. Which analysis is most accurate?

A.	The varied explanations may share a root cause, namely that projects start without a readiness and adoption plan, so analyzing them together would reveal the systemic issue

B.	The causes are unrelated, so each case needs separate treatment

C.	The problem is only the lack of training, since it appears in one explanation

D.	The recurring pattern is a coincidence and needs no analysis

Key: A.  Different symptoms recurring across projects often point to a common process weakness. All three explanations are missing readiness preparation.

R-51  Sub-competency 12.2 | Creation | Difficult | JD: T43, T42, M65

Which is the best design for a mechanism through which lessons and findings from monitoring and evaluation feed back into the Desk's planning and policy inputs?

A.	A folder in which project teams store final reports for anyone who wishes to read them

B.	An annual meeting where lessons are discussed orally with no records

C.	A requirement that each staff member writes a private reflection on each project

D.	A periodic review in which findings and lessons are recorded in a shared repository, classified by theme, presented to management with recommended changes, and reflected in the next plan and guidelines, with follow-up on implementation

Key: D.  An effective feedback loop records, classifies, presents and acts on lessons, and follows up on their use. The alternatives store or discuss lessons without ensuring action.

## Key distribution (Results items)

A: 13   B: 12   C: 13   D: 13

# 8. Coverage check

| ID | Sub-competency | Blueprint | Written | Status |
| --- | --- | --- | --- | --- |
| 1.1 | Aligning plans and roadmaps with national strategy | 8 | 8 | Matches blueprint |
| 1.2 | Formulating and revising policies, strategies and standards | 6 | 6 | Matches blueprint |
| 2.1 | Annual and operational planning | 7 | 7 | Matches blueprint |
| 3.1 | Resource estimation, technical specifications and procurement inputs | 5 | 5 | Matches blueprint |
| 4.1 | Using digital tools and information systems for Desk management | 5 | 5 | Matches blueprint |
| 5.1 | Data-center, cloud and shared infrastructure | 7 | 7 | Matches blueprint |
| 5.2 | Network, connectivity, security and resilience | 7 | 7 | Matches blueprint |
| 6.1 | Research, needs assessment and evidence-based analysis | 7 | 7 | Matches blueprint |
| 6.2 | Technical review, standards and interoperability | 6 | 6 | Matches blueprint |
| 7.1 | Professional ethics and accountability in public ICT work | 5 | 5 | Matches blueprint |
| 8.1 | Leading and developing the Desk team | 6 | 6 | Matches blueprint |
| 9.1 | Evidence-based decisions and options analysis | 7 | 7 | Matches blueprint |
| 9.2 | Risk-informed decisions and corrective action | 6 | 6 | Matches blueprint |
| 10.1 | Monitoring plan and project implementation | 7 | 7 | Matches blueprint |
| 10.2 | Monitoring availability, capacity, utilization and accessibility | 7 | 7 | Matches blueprint |
| 11.1 | Evaluating utilization and results | 7 | 7 | Matches blueprint |
| 11.2 | Compliance and standards assessment | 7 | 7 | Matches blueprint |
| 12.1 | Service-user and stakeholder communication and feedback | 5 | 5 | Matches blueprint |
| 12.2 | Lessons learned and knowledge feedback loop | 5 | 5 | Matches blueprint |
|  | Total | 120 | 120 |  |

## Cognitive level and difficulty of the written items

|  | Re | Un | Ap | An | Ev | Cr | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Easy | 10 | 14 | 0 | 0 | 0 | 0 | 24 |
| Moderate | 0 | 13 | 30 | 17 | 0 | 0 | 60 |
| Difficult | 0 | 0 | 14 | 11 | 7 | 4 | 36 |
| Total | 10 | 27 | 44 | 28 | 7 | 4 | 120 |

Answer-key distribution across all 120 items: A 30, B 29, C 30, D 31.